## Burn down chart
Release Burndown
Sprints completed | Expected Story Points Remaining | Actual Story Points Remaining
0 | 41 | 41
1 |  | 17
2 |  | 24
4 | 0
Sprint 1 Burndown
Sprint Days Remaining | Ideal Tasks Remaining | Actual Tasks Remaining
20 | 31 | 31
19 |  | 31
18 |  | 31
17 |  | 31
16 |  | 29
15 |  | 29
14 |  | 28
13 |  | 27
12 |  | 27
11 |  | 27
10 |  | 27
9 |  | 24
8 |  | 23
7 |  | 23
6 |  | 21
5 |  | 20
4 |  | 17
3 |  | 17
2 |  | 16
1 |  | 16
0 | 0
ALSO DO A SPRINT 2 BURNDOWN AS WELL